## Sheet1
MPW run # | [6 empty] | SP18 |  |  | SP19 |  |  | SP20 |  |  | SP21 |  |  | SP22 |  |  | SP23 |  |  | SP24 |  |  | SP25 |  |  | SP26 |  |  | SP27 |  |  | SP28 |  |  | SP29
Month | [6 empty] | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
ID | Title | Responsible | Contrib. partner | Due Times |  |  | SP18 9: 2016; SP19 1: 2017; SP23 1: 2018; SP27 1: 2019
Work Package 1 - Market Demands | [6 empty] | SP18 9: Review Report I; SP21 7: Review Report II; SP23 1: Review Report III
WP1.M1 | Demonstrator definitions – linking products to building blocks | Aura | Effect, Technobis | 2017-03-01 | bar: SP20 3
WP1.M2 | Survey of requirements and building blocks | Weiming |  | 2018-11-01 | bar: SP26 11
WP1.M3 | Platform roadmap | Aura |  | 2018-09-01 | bar: SP26 9
WP1.M4 | Key performance Indicators for MPWs | Aura |  | 2017-09-01 | bar: SP22 9
WP1.M5 | Training and Outreach | Aura |  | 2017-06-01 | bar: SP21 6
Work Package 2 - Pilot Line
ID | Title | Responsible |  | Due Times
WP2.M0.1 | WP2 Project Charter | Roel |  | 2017-06-01 | bar: SP21 6
WP2.M0.2 | WP2 Milestone Planning | Roel |  | 2017-06-01 | bar: SP21 6
WP 2.1 | Generic BB Data and Characterization
WP2.1.M1.1 | List of Generic MPW parameters for data monitoring & MPW cadence | Roel |  | 2017-06-01 | bar: SP21 6
WP2.1.M1.2 | Generic Update Q3'16 - Q2'17 Data up to and including SP19 (1st 3inch MPW) | Roel |  | 2017-06-01 | bar: SP21 6
WP2.1.M?? | T.B.D. | Roel
WP 2.2 | General Improvements
WP2.2.M1.1 | Metallization - Lift-Off improvements | Roel |  | 2017-06-01 | bar: SP21 6
WP2.2.M1.? | T.B.D. | Roel
Laser Threshold & Passivation improvements
WP2.2.M2.1 | Threshold Current & Passivation - Dielectric Material Improvements | Roel |  | 2017-06-01 | bar: SP21 6
WP2.2.M2.2 | Threshold Current & Passivation - Integration Improvements | Roel |  | 2017-06-01 | bar: SP21 6
WP2.2.M2.3 | Threshold Current & Passivation - Passivation Integrity/Integration Improvements update | Roel |  | 2017-12-01 | bar: SP23 12
Planarisation
WP2.2.M3.1 | Polyimide Planarisation sequence on SP20 | Roel |  | 2017-09-01 | bar: SP22 9
WP2.2.M3.2 | Dummy Structures/Tiling (on SP22) | Roel |  | 2017-12-01 | bar: SP23 12
WP2.2.M3.? | T.B.D. | Roel
Waveguide Loss improvements
WP2.2.M4.1 | T.B.D. | Roel
WP 2.3 | New Building Blocks (from WP3) Commercially Avaliable on MPW
WP2.3.M1.1 | DBR laser | Roel |  | 2017-09-01 | bar: SP22 9
WP2.3.M1.2 | SI substrate | Roel |  | 2017-12-01 | bar: SP23 12
WP2.3.M1.3 | Effect MQW | Roel |  | 2018-03-01 | bar: SP24 3
WP2.3.M1.4 | Spotsize Convertor | Roel |  | 2018-06-01 | bar: SP25 6
WP2.3.M1.5 | Al MQW | Roel |  | 2019-03-01 | bar: SP28 3
Work Package 3 - Building Block Improvement
ID | Title | Responsible |  | Due Times
WP 3.1 | BB Design
WP3.1.M0 | Technology and Design Concept | Weiming, Ronald |  | 2017-12-01 |  |  | SP19 12: postponed from Bright
WP3.1.R0 | Analysis and Design | Weiming, Ronald |  | 2017-12-01 |  |  | SP21 6: postponed from Bright
WP3.1.M1 | Mask Design Tape-out I | Weiming, Ronald |  | 2017-06-01 | bar: SP21 6
WP3.1.R1 | BB Results I | Weiming, Ronald |  | 2018-03-01 | bar: SP24 3
WP3.1.M2 | Mask Design Tape-out II | Weiming, Ronald |  | 2018-09-01 | bar: SP26 9
WP3.1.R2 | BB Results II | Weiming, Ronald |  | 2019-06-01 | bar: SP29 6
WP 3.2 | PDK Content
WP3.2.M0 | State of the PDK | Rui |  | 2016-12-01 | bar: SP19 12
WP3.2.M1 | Definition of basic BB figure of merits | Rui |  | 2017-03-01 | bar: SP20 3
WP3.2.M2 | Definition of composite BB FoM | Weiming |  | 2017-03-01 | bar: SP20 3
WP3.2.R0 | Definition of measurement procedures | Weiming |  | 2017-06-01 | bar: SP21 6
WP3.2.R1 | PDK upgrade with new advanced BB | Rui |  | 2018-03-01 | bar: SP24 3
WP3.2.R2 | Compact Models | Rui |  | 2018-06-01 | bar: SP25 6
WP 3.3 | BB Characterization
WP3.3.R0 | Design of Standard MPW BB test cell | Weiming |  | 2017-03-01 | bar: SP20 3
WP3.3.M0 | Report on standard MPW BB cell results | Rui |  | Every MPW | bar: SP23 1; SP24 4; SP25 7; SP26 10; SP27 1; SP28 4; SP29 7
WP3.3.R1 | Design of composite BB test cell | Weiming |  | 2017-09-01 | bar: SP22 9
WP3.3.M1 | Report on composite test cell results | Weiming |  | 2018-03-01 | [38 empty] | 8 | bar: SP24 3
WP 3.4 | Design Environment
WP3.4.DF.R0 | Design Flow document | Marcel |  | 2017-03-01 | 2018-01-01 | 2018-11-01 | bar: SP20 3; SP23 1; SP26 11
WP3.4.DF.R1 | Improvement points | Marcel |  | 2017-04-01 | 2018-02-01 | 2018-12-01 | bar: SP20 4; SP23 2; SP27 12
WP3.4.DF.M0 | Implementation of selected improvement points | Marcel |  | 2018-01-01 | 2018-11-01 | 2019-08-01 | bar: SP23 1; SP26 11; SP29 8
WP3.4.DF.R2 | Final Design flow Document | Marcel |  | 2019-08-01 | bar: SP29 8
WP3.4.EF.R0 | Exectution Flow document | Ronald |  | 2017-05-01 | 2018-03-01 | 2019-01-01 | bar: SP20 5; SP24 3; SP27 1
WP3.4.EF.M0 | Implementation of an Execution DB | Ronald |  | 2018-03-01 | 2019-01-01 | 2019-08-01 | bar: SP20 3; SP27 1; SP29 8
WP3.4.EF.R1 | Final Execution Flow document | Ronald |  | 2019-08-01 | bar: SP29 8
WP3.4.PDA.M0 | Development of PDAflow template | Marcel |  | 2017-03-01 | 2018-05-01 | 2019-07-01 | bar: SP20 3; SP24 5; SP29 7
WP3.4.PDA.M1 | Implementation of first building block | Marcel |  | 2017-04-01 | bar: SP20 4
WP3.4.PDA.R0 | Full documentation of template | Marcel |  | 2017-03-01 | 2018-05-01 | 2019-07-01 | bar: SP20 3; SP24 5; SP29 7
WP3.4.PDA.M2 | Update of Smart and TU/e PDK | Marcel |  | 2018-06-01 | 2018-12-01 | 2019-08-01 | bar: SP25 6; SP27 12; SP29 8
WP3.4.DRC.R0 | DRC requirement report | Marcel |  | 2017-05-01 | bar: SP20 5
WP3.4.DRC.R1 | Documentation of DRC capability | Marcel |  | 2017-08-01 | 2018-08-01 | 2019-06-01 | bar: SP21 8; SP25 8; SP29 6
WP3.4.DRC.M0 | DRC Implementation in PDKs | Marcel, Ronald |  | 2017-11-01 | 2018-09-01 | 2019-07-01 | bar: SP22 11; SP26 9; SP29 7
WP3.4.DRC.R2 | Implementation of new DRC functionality | Marcel |  | 2018-08-01 | 2019-06-01 | bar: SP25 8; SP29 6
WP 3.5 | Demonstrator Design
WP3.5.R0 | 400G Transmitter concept | Saeed |  | 2017-03-01 | bar: SP20 3
WP3.5.R1 | Fiber sensing chip concept | Pim |  | 2017-03-01 | bar: SP20 3
WP3.5.M0 | 400 G Transmitter Design | Saeed |  | 2018-09-01 | bar: SP26 9
WP3.5.M1 | Fiber Sensing Chip Design | Ronald |  | 2018-09-01 | bar: SP26 9
WP3.5.M2 | Results of 400G Transmitter | Saeed |  | 2019-06-01 | bar: SP29 6
WP3.5.M3 | Results of fiber sensing chip | Pim |  | 2019-06-01 | bar: SP29 6
Work Package 4 - Process Improvement
ID | Title | Responsible |  | Due Times
WP4.M 0.1 | Specific tasks and milestones defined; WP started | Victor |  | 2016-12-01 | bar: SP19 12
WP4.M 0.2 | Quantifiable criteria for each milestone defined | Victor |  | 2017-03-01 | bar: SP20 3
WP4.1 | Al-MQW bsed modulators
WP4.M 1.1 | Designed MQW characterized, shallow-etch modulators demonstrated | Victor |  | 2018-03-30 | bar: SP24 3
WP4.M 1.2 | Etching and passivation processes developed: ready for MPW validation | Victor |  | 2018-06-30 | bar: SP25 6
WP4.M 1.3 | Modulator validated in MPW: ready for release | Smart |  | 2019-03-30 | bar: SP28 3
WP4.D 1.4 | Report on process optimization and insights for Al-based SOA and 100 Gbps modulators | Victor |  | 2019-06-30 | bar: SP29 6
WP 4.2 | Zn-Diffusion based A/P integration
WP4.M 2.1 | Zn-diffusion time determined: ready for joint MPW validation | Rene |  | 2018-01-31 | bar: SP23 1
WP4.M 2.2 | Zn-diffusion process validated in joint MPW: ready for transfer to Smart | Rene |  | 2019-01-31 | bar: SP27 1
WP4.M 2.3 | Zn-diffusion process transferred and validated in MPW: ready for release | Smart |  | 2019-08-30 | bar: SP29 8
WP4.D 2.4 | Report on process integration and device characterization | Rene, Victor |  | 2019-08-30 | bar: SP29 8
WP 4.3 | Thick insulation and RF lines
WP4.M 3.1 | BCB insulation and metal plating tested: ready for joint MPW validation | Tjibbe |  | 2018-02-28 | bar: SP23 2
WP4.M 3.2 | Process validated in joint MPW (post-processing): ready for transfer | Tjibbe |  | 2018-06-29 | bar: SP25 6
WP4.M 3.3 | Process transferred and validated in MPW: ready for release | Smart |  | 2018-09-28 | bar: SP26 9
WP4.D 3.4 | Report on process integration, insights for 100 Gbps RF lines, and for multi-layer routing | Tjibbe, Victor |  | 2018-12-31 | bar: SP27 12
WP 4.4 | DUV Lithography and etching optimization
WP4.M 4.1 | DUV lithography introduced to MPW | Smart |  | 2017-06-30 | bar: SP21 6
WP4.M 4.2 | Etching process optimized, ready for transfer to MPW | Victor |  | 2018-03-31 | bar: SP24 3
WP4.M 4.3 | DUV lithography introduced to Triplex platform | Lionix |  | 2019-01-01 | bar: SP27 1
WP4.D 4.4 | Report on process integration (lithography and etching) in MPW | Smart |  | 2019-01-31 | bar: SP27 1
WP 4.5 | Stepper Lithorgraphy integration
WP4.M 5.1 | Process developed for AZ and MaN based lithography | Robert |  | 2017-08-31 | bar: SP21 8
WP4.M 5.2 | Overlay tested and optimized | Robert |  | 2018-01-31 | bar: SP23 1
WP4.M 5.3 | Process introduced to Smart MPW | Smart |  | 2018-09-30 | bar: SP26 9
WP4.D 5.4 | Report on process integration, insights for fabricating new BBs | Robert, Victor |  | 2018-12-31 | bar: SP27 12